## Task Database
Task ID | Tier | Category | Sub-heading | Source Sentence | Task | Lead | Track | Recommendation Only | Connection Type | Connected Task IDs | Connection Pending Confirmation | Notes
F-SW-01a-01 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Identify applicable code and regulatory requirements (ADA, IBC, fire, OSHA, etc.) | Consultant | Single | No | — |  | No
F-SW-01a-02 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Audit existing signage against requirements to confirm gaps | Consultant | Single | No | Dependency | F-SW-01a-01 | No | Requires F-SW-01a-01 to be complete
F-SW-01a-03 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Determine authority having jurisdiction (AHJ) and confirm approval process | Consultant | Single | No | — |  | No
F-SW-01a-04 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Specify sign types, sizes, content, and placement per code | Consultant | Single | No | Dependency | F-SW-01a-02 | No
F-SW-01a-05 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Remove existing non-compliant signage | Third-party | Single | No | Dependency | F-SW-01a-04 | No
F-SW-01a-06 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Fabrication | Third-party | Single | No | Dependency | F-SW-01a-04 | No | Synergy candidate: may share fabrication run with F-SW-01b and F-SW-01c
F-SW-01a-07 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-01a-06 | No
F-SW-01a-08 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create missing code and regulatory signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-01a-07 | No
F-SW-01b-01 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Distinguish from temporary signage currently in use and identify replacement scope | Consultant | Single | No | Dependency | F-SW-01a-02 | No | Compliance audit informs this
F-SW-01b-02 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Define what qualifies as safety signage (egress, hazard, PPE, etc.) | Consultant | Single | No | — |  | No
F-SW-01b-03 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Select durable materials and finishes appropriate for environment | Consultant | Single | No | Synergy | F-SW-01c-02 | Yes | Synergy candidate: material selection may align with visual language task
F-SW-01b-04 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Design or specify sign content and visual format | Consultant | Single | No | Dependency | F-SW-01c-02 | No | Must align with visual language established in F-SW-01c
F-SW-01b-05 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Remove existing temporary or non-permanent signage | Third-party | Single | No | Synergy | F-SW-01a-05 | Yes | Synergy candidate: same installer mobilization as F-SW-01a-05
F-SW-01b-06 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Fabrication | Third-party | Single | No | Synergy | F-SW-01a-06 | Yes | Synergy candidate: same fabrication run as F-SW-01a-06
F-SW-01b-07 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-01b-06 | No
F-SW-01b-08 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create permanent safety signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-01b-07 | No
F-SW-01c-01 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Audit all existing safety signage for inconsistencies in color, typography, iconography, size, and tone | Consultant | Single | No | Synergy | F-SW-01a-02 | Yes | Synergy candidate: may be conducted simultaneously with compliance audit
F-SW-01c-02 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Develop a holistic, coherent design direction for safety signage | Consultant | Single | No | Dependency | F-SW-01c-01 | No | Design direction precedes standards manual — formalized in Advanced phase (A-SW-22b)
F-SW-01c-03 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Remove existing inconsistent signage | Third-party | Single | No | Synergy | F-SW-01a-05, F-SW-01b-05 | Yes | Synergy candidate: same installer mobilization
F-SW-01c-04 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Fabrication | Third-party | Single | No | Synergy | F-SW-01a-06, F-SW-01b-06 | Yes | Synergy candidate: same fabrication run
F-SW-01c-05 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-01c-04 | No
F-SW-01c-06 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-01c-05 | No
F-SW-01c-07 | Foundational | Signage and Wayfinding | Code, life-safety, and required signage | Create a consistent visual language for safety signage | Formalize design direction into sign standards manual | Consultant | Single | No | Dependency | F-SW-01c-02 | No | Cross-tier: executes in Advanced phase — see A-SW-22b
F-SW-02a-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Improve the campus-wide naming, numbering, and zoning system | Audit existing naming, numbering, and zoning conventions across all buildings | Consultant | Single | No | — |  | No | Redesign from scratch — audit establishes baseline to depart from
F-SW-02a-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Improve the campus-wide naming, numbering, and zoning system | Define new naming, numbering, and zoning framework | Consultant | Single | No | Dependency | F-SW-02a-01 | No | Cross-tier: output feeds all Intermediate and Advanced wayfinding tasks
F-SW-02a-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Improve the campus-wide naming, numbering, and zoning system | Conduct stakeholder alignment sessions (facilities, IT, leadership) | Consultant | Single | No | Dependency | F-SW-02a-02 | No | Approval authority must be established before names are finalized
F-SW-02a-04 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Improve the campus-wide naming, numbering, and zoning system | Validate framework for intuitive comprehension (user testing and consultant review — parallel tracks; see F-SW-02b) | Consultant | Single | No | Dependency | F-SW-02a-02 | No
F-SW-02a-05 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Improve the campus-wide naming, numbering, and zoning system | Document and publish final nomenclature system | Consultant | Single | No | Dependency | F-SW-02a-03, F-SW-02a-04 | No | Prerequisite for F-SW-02b through 02f and all naming-dependent Intermediate tasks
F-SW-02b-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Update zone and neighborhood naming so that it is intuitive and easily comprehensible | User testing of proposed zone names with representative employee sample | Consultant | Parallel A | No | Dependency | F-SW-02a-02 | No | Parallel track — runs alongside consultant review (F-SW-02b-02)
F-SW-02b-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Update zone and neighborhood naming so that it is intuitive and easily comprehensible | Consultant review and refinement of proposed zone names | Consultant | Parallel B | No | Dependency | F-SW-02a-02 | No | Parallel track — runs alongside user testing (F-SW-02b-01)
F-SW-02b-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Update zone and neighborhood naming so that it is intuitive and easily comprehensible | Synthesize findings and finalize zone and neighborhood names | Consultant | Single | No | Dependency | F-SW-02b-01, F-SW-02b-02 | No | Parallel tracks converge here
F-SW-02c-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Align names across signage, maps, and booking tools | Identify all touchpoints where names appear (signage, maps, booking tools, directories) | Consultant | Single | No | Dependency | F-SW-02a-05 | No
F-SW-02c-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Align names across signage, maps, and booking tools | Define requirements for name updates across each touchpoint | Consultant | Single | No | Dependency | F-SW-02c-01 | No
F-SW-02c-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Align names across signage, maps, and booking tools | Brief IT and facilities on digital and physical update requirements | Consultant | Single | No | Dependency | F-SW-02c-02 | No | Handoff — IT leads digital implementation beyond this
F-SW-02c-04 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Align names across signage, maps, and booking tools | Client/IT implements updates and monitors alignment | Client / IT | Single | No | Dependency | F-SW-02c-03 | No | Client-led beyond handoff
F-SW-02d-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Rename duplicate or conflicting rooms | Identify all duplicate and conflicting room names across campus | Consultant | Single | No | Dependency | F-SW-02a-05 | No
F-SW-02d-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Rename duplicate or conflicting rooms | Propose new names aligned to nomenclature framework | Consultant | Single | No | Dependency | F-SW-02d-01 | No
F-SW-02d-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Rename duplicate or conflicting rooms | Conduct stakeholder alignment (facilities, IT, leadership) for approval | Consultant | Single | No | Dependency | F-SW-02d-02 | No | Approval required before any physical or digital changes
F-SW-02d-04 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Rename duplicate or conflicting rooms | Update physical signage to reflect new names | Third-party | Single | No | Dependency | F-SW-02d-03 | No
F-SW-02d-05 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Rename duplicate or conflicting rooms | Brief IT to update booking systems and digital directories | Consultant | Single | No | Dependency | F-SW-02d-03 | No | Handoff to IT
F-SW-02e-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize floor numbering conventions | Audit existing floor numbering across all buildings | Consultant | Single | No | Synergy | F-SW-02a-01 | Yes | Synergy candidate: same audit pass as F-SW-02a-01
F-SW-02e-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize floor numbering conventions | Define standard floor numbering convention aligned to nomenclature framework | Consultant | Single | No | Dependency | F-SW-02e-01, F-SW-02a-02 | No
F-SW-02e-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize floor numbering conventions | Apply to physical signage, elevator cabs, and digital systems | Third-party / IT | Single | No | Dependency | F-SW-02e-02 | No | Cross-system — physical and digital tracks run in parallel
F-SW-02f-01 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize building color nomenclature | Audit existing building color naming and usage across campus | Consultant | Single | No | Synergy | F-SW-02a-01 | Yes | Synergy candidate: same audit pass as F-SW-02a-01
F-SW-02f-02 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize building color nomenclature | Define standardized color nomenclature aligned to wayfinding zones | Consultant | Single | No | Dependency | F-SW-02f-01, F-SW-02a-02 | No
F-SW-02f-03 | Foundational | Signage and Wayfinding | Campus-wide nomenclature | Standardize building color nomenclature | Apply to signage, maps, and digital systems | Third-party / IT | Single | No | Dependency | F-SW-02f-02 | No
F-SW-03a-01 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Inventory all unlabeled major spaces across campus | Consultant | Single | No | Synergy | F-SW-02a-01 | Yes | Synergy candidate: same audit pass
F-SW-03a-02 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Assign names and numbers per nomenclature framework | Consultant | Single | No | Dependency | F-SW-02a-05, F-SW-03a-01 | No | Cannot assign until nomenclature system is finalized
F-SW-03a-03 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Get stakeholder approval on assignments | Consultant | Single | No | Dependency | F-SW-03a-02 | No
F-SW-03a-04 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Fabrication | Third-party | Single | No | Dependency | F-SW-03a-03 | No
F-SW-03a-05 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-03a-04 | No
F-SW-03a-06 | Foundational | Signage and Wayfinding | Key destination identification | Name and number unlabeled major spaces | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-03a-05 | No
F-SW-03b-01 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Inventory all unlabeled meeting spaces | Consultant | Single | No | Synergy | F-SW-03a-01 | Yes | Synergy candidate: same inventory pass
F-SW-03b-02 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Assign names per nomenclature framework and confirm with stakeholders | Consultant | Single | No | Dependency | F-SW-02a-05, F-SW-03b-01 | No
F-SW-03b-03 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Design meeting space identification signage | Consultant | Single | No | — |  | No
F-SW-03b-04 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Remove any existing ad hoc or temporary labels | Third-party | Single | No | Synergy | F-SW-03a-04 | Yes | Synergy candidate: same installer mobilization
F-SW-03b-05 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Fabrication | Third-party | Single | No | Synergy | F-SW-03a-04 | Yes | Synergy candidate: same fabrication run
F-SW-03b-06 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-03b-05 | No
F-SW-03b-07 | Foundational | Signage and Wayfinding | Key destination identification | Create signage for unlabeled meeting spaces | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-03b-06 | No
F-SW-03c-01 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Inventory departments and teams and map to physical locations | Consultant | Single | No | Synergy | F-SW-03a-01 | Yes | Synergy candidate: same audit pass
F-SW-03c-02 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Define identifier format and content per nomenclature and brand standards | Consultant | Single | No | Dependency | F-SW-02a-05 | No
F-SW-03c-03 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Get stakeholder approval | Consultant | Single | No | Dependency | F-SW-03c-02 | No
F-SW-03c-04 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Fabrication | Third-party | Single | No | Synergy | F-SW-03b-05 | Yes | Synergy candidate: same fabrication run
F-SW-03c-05 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-03c-04 | No
F-SW-03c-06 | Foundational | Signage and Wayfinding | Key destination identification | Add department and team location identifiers | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-03c-05 | No
F-SW-04a-01 | Foundational | Signage and Wayfinding | Accessible navigation | Identify and document all accessible routes | Define scope of accessibility audit and need for third-party consultant | Consultant | Single | No | — |  | No | Handoff point — third-party leads audit
F-SW-04a-02 | Foundational | Signage and Wayfinding | Accessible navigation | Identify and document all accessible routes | Select and brief third-party accessibility consultant | Consultant | Single | No | Dependency | F-SW-04a-01 | No
F-SW-04a-03 | Foundational | Signage and Wayfinding | Accessible navigation | Identify and document all accessible routes | Third-party conducts accessibility audit of all routes | Third-party | Single | No | Dependency | F-SW-04a-02 | No
F-SW-04a-04 | Foundational | Signage and Wayfinding | Accessible navigation | Identify and document all accessible routes | Third-party produces sketched map documentation of accessible routes | Third-party | Single | No | Dependency | F-SW-04a-03 | No | Deliverable format: sketched maps
F-SW-04a-05 | Foundational | Signage and Wayfinding | Accessible navigation | Identify and document all accessible routes | Incorporate accessible route findings into consultant deliverables | Consultant | Single | No | Dependency | F-SW-04a-04 | No | Cross-tier: feeds I-SW and A-SW accessible wayfinding tasks
F-SW-05a-01 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Audit existing garage naming, numbering, and identification signage | Consultant | Single | No | Synergy | F-SW-02a-01 | Yes | Synergy candidate: same audit pass as campus nomenclature
F-SW-05a-02 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Define updated naming and identification conventions per nomenclature framework | Consultant | Single | No | Dependency | F-SW-02a-05, F-SW-05a-01 | No
F-SW-05a-03 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Remove existing non-standard identification elements | Third-party | Single | No | Dependency | F-SW-05a-02 | No
F-SW-05a-04 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Fabrication | Third-party | Single | No | Synergy | F-SW-05b-03, F-SW-05c-02, F-SW-05d-03 | Yes | Synergy candidate: all garage signage in one fabrication run
F-SW-05a-05 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-05a-04 | No
F-SW-05a-06 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Improve garage naming conventions and identifications | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-05a-05 | No
F-SW-05b-01 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create level identification signage | Define level identification format per nomenclature and visual language | Consultant | Single | No | Dependency | F-SW-02a-05 | No
F-SW-05b-02 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create level identification signage | Design level identification signage | Consultant | Single | No | Dependency | F-SW-05b-01 | No
F-SW-05b-03 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create level identification signage | Fabrication | Third-party | Single | No | Synergy | F-SW-05a-04 | Yes | Synergy candidate: same garage fabrication run
F-SW-05b-04 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create level identification signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-05b-03 | No
F-SW-05b-05 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create level identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-05b-04 | No
F-SW-05c-01 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create elevator identification signage | Design elevator identification signage per nomenclature and code requirements | Consultant | Single | No | Dependency | F-SW-02a-05 | No
F-SW-05c-02 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create elevator identification signage | Fabrication | Third-party | Single | No | Synergy | F-SW-05a-04 | Yes | Synergy candidate: same garage fabrication run
F-SW-05c-03 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create elevator identification signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-05c-02 | No
F-SW-05c-04 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create elevator identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-05c-03 | No
F-SW-05d-01 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create pedestrian safety signage | Define pedestrian safety signage requirements (crosswalks, speed zones, hazard areas) | Consultant | Single | No | Dependency | F-SW-01a-01 | No | Feeds from code/regulatory requirements
F-SW-05d-02 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create pedestrian safety signage | Design pedestrian safety signage aligned to visual language | Consultant | Single | No | Dependency | F-SW-01c-02 | No | Visual language must be established first
F-SW-05d-03 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create pedestrian safety signage | Fabrication | Third-party | Single | No | Synergy | F-SW-05a-04 | Yes | Synergy candidate: same garage fabrication run
F-SW-05d-04 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create pedestrian safety signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-05d-03 | No
F-SW-05d-05 | Foundational | Signage and Wayfinding | Parking garage navigation and safety | Create pedestrian safety signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-05d-04 | No
F-SW-06a-01 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Audit all main entrances for clarity, visibility, and signage adequacy | Consultant | Single | No | — |  | No
F-SW-06a-02 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Design entrance clarification signage per visual language | Consultant | Single | No | Dependency | F-SW-01c-02 | No
F-SW-06a-03 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Remove existing unclear or conflicting entrance signage | Third-party | Single | No | — |  | No
F-SW-06a-04 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Fabrication | Third-party | Single | No | Synergy | F-SW-06b-03, F-SW-06d-03 | Yes | Synergy candidate: arrival system fabrication run
F-SW-06a-05 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-06a-04 | No
F-SW-06a-06 | Foundational | Signage and Wayfinding | Arrival and entry system | Clarify main building entrances | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-06a-05 | No
F-SW-06b-01 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor, vendor, and new hire entrances | Define designation logic for each user type in coordination with facilities and security | Consultant | Single | No | — |  | No
F-SW-06b-02 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor, vendor, and new hire entrances | Design designation signage per user type | Consultant | Single | No | Dependency | F-SW-06b-01 | No
F-SW-06b-03 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor, vendor, and new hire entrances | Fabrication | Third-party | Single | No | Synergy | F-SW-06a-04 | Yes | Synergy candidate: same arrival system fabrication run
F-SW-06b-04 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor, vendor, and new hire entrances | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-06b-03 | No
F-SW-06b-05 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor, vendor, and new hire entrances | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-06b-04 | No
F-SW-06c-01 | Foundational | Signage and Wayfinding | Arrival and entry system | Update Google Maps destinations | Identify all campus locations currently listed on Google Maps | Consultant | Single | No | — |  | No
F-SW-06c-02 | Foundational | Signage and Wayfinding | Arrival and entry system | Update Google Maps destinations | Define correct destination entries per nomenclature framework | Consultant | Single | No | Dependency | F-SW-02a-05, F-SW-06c-01 | No
F-SW-06c-03 | Foundational | Signage and Wayfinding | Arrival and entry system | Update Google Maps destinations | Brief client on Google Maps update process and transfer responsibility | Consultant | Single | No | Dependency | F-SW-06c-02 | No | Handoff — client leads update
F-SW-06c-04 | Foundational | Signage and Wayfinding | Arrival and entry system | Update Google Maps destinations | Client updates Google Maps listings | Client | Single | No | Dependency | F-SW-06c-03 | No | Client-led beyond handoff
F-SW-06d-01 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor drop-off locations and add identification signage | Identify and confirm drop-off zones with facilities and security | Consultant | Single | No | Dependency | F-SW-06b-01 | No
F-SW-06d-02 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor drop-off locations and add identification signage | Design drop-off identification and directional signage | Consultant | Single | No | Dependency | F-SW-06d-01 | No
F-SW-06d-03 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor drop-off locations and add identification signage | Fabrication | Third-party | Single | No | Synergy | F-SW-06a-04 | Yes | Synergy candidate: same arrival system fabrication run
F-SW-06d-04 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor drop-off locations and add identification signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | F-SW-06d-03 | No
F-SW-06d-05 | Foundational | Signage and Wayfinding | Arrival and entry system | Designate visitor drop-off locations and add identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | F-SW-06d-04 | No