## Task Database
Task ID | Tier | Category | Sub-heading | Source Sentence | Task | Lead | Track | Recommendation Only | Connection Type | Connected Task IDs | Connection Pending Confirmation | Notes
F-BE-07a-01 | Foundational | Brand Expression | Workplace brand definition | Define workplace brand categories | Audit existing brand usage across all buildings to understand current informal categories | Consultant | Single | No | — |  | No | May be new taxonomy or codification of existing — audit determines which
F-BE-07a-02 | Foundational | Brand Expression | Workplace brand definition | Define workplace brand categories | Define new or revised workplace brand category structure | Consultant | Single | No | Dependency | F-BE-07a-01 | No | Cross-tier: output feeds all Intermediate and Advanced brand expression tasks
F-BE-07a-03 | Foundational | Brand Expression | Workplace brand definition | Define workplace brand categories | Validate category structure with client stakeholders | Consultant | Single | No | Dependency | F-BE-07a-02 | No
F-BE-07b-01 | Foundational | Brand Expression | Workplace brand definition | Define campaign use in workplace environments | Inventory current campaign usage across campus | Consultant | Single | No | Synergy | F-BE-07a-01 | Yes | Synergy candidate: same brand audit pass
F-BE-07b-02 | Foundational | Brand Expression | Workplace brand definition | Define campaign use in workplace environments | Define guidelines for appropriate campaign use by space type | Consultant | Single | No | Dependency | F-BE-07a-02 | No
F-BE-07b-03 | Foundational | Brand Expression | Workplace brand definition | Define campaign use in workplace environments | Document and distribute guidelines to client | Consultant | Single | No | Dependency | F-BE-07b-02 | No
F-BE-07c-01 | Foundational | Brand Expression | Workplace brand definition | Define art use in workplace environments | Inventory existing art installations across campus | Consultant | Single | No | Synergy | F-BE-07a-01 | Yes | Synergy candidate: same brand audit pass
F-BE-07c-02 | Foundational | Brand Expression | Workplace brand definition | Define art use in workplace environments | Define guidelines for art curation and placement by space type | Consultant | Single | No | Dependency | F-BE-07a-02 | No | Cross-tier: feeds I-BE art and cultural programs
F-BE-07c-03 | Foundational | Brand Expression | Workplace brand definition | Define art use in workplace environments | Document and distribute guidelines | Consultant | Single | No | Dependency | F-BE-07c-02 | No
F-BE-07d-01 | Foundational | Brand Expression | Workplace brand definition | Define product display use in workplace environments | Inventory existing product display installations | Consultant | Single | No | Synergy | F-BE-07a-01 | Yes | Synergy candidate: same brand audit pass
F-BE-07d-02 | Foundational | Brand Expression | Workplace brand definition | Define product display use in workplace environments | Define guidelines for product display by space type | Consultant | Single | No | Dependency | F-BE-07a-02 | No | Cross-tier: feeds I-BE product display tasks
F-BE-07d-03 | Foundational | Brand Expression | Workplace brand definition | Define product display use in workplace environments | Document and distribute guidelines | Consultant | Single | No | Dependency | F-BE-07d-02 | No
F-BE-08a-01 | Foundational | Brand Expression | Outdated content removal | Remove outdated logos | Audit all campus locations for outdated logo usage | Consultant | Single | No | Synergy | F-BE-07a-01 | Yes | Synergy candidate: same brand audit pass
F-BE-08a-02 | Foundational | Brand Expression | Outdated content removal | Remove outdated logos | Document locations and removal scope | Consultant | Single | No | Dependency | F-BE-08a-01 | No
F-BE-08a-03 | Foundational | Brand Expression | Outdated content removal | Remove outdated logos | Remove outdated logos | Third-party | Single | No | Synergy | F-BE-08b-02, F-BE-08c-02 | Yes | Synergy candidate: same removal mobilization as slogans and graphics
F-BE-08a-04 | Foundational | Brand Expression | Outdated content removal | Remove outdated logos | Quality control / punchwalk | Consultant | Single | No | Dependency | F-BE-08a-03 | No
F-BE-08b-01 | Foundational | Brand Expression | Outdated content removal | Remove outdated slogans | Audit all campus locations for outdated slogan usage | Consultant | Single | No | Synergy | F-BE-08a-01 | Yes | Synergy candidate: same audit pass
F-BE-08b-02 | Foundational | Brand Expression | Outdated content removal | Remove outdated slogans | Remove outdated slogans | Third-party | Single | No | Synergy | F-BE-08a-03 | Yes | Synergy candidate: same removal mobilization
F-BE-08b-03 | Foundational | Brand Expression | Outdated content removal | Remove outdated slogans | Quality control / punchwalk | Consultant | Single | No | Dependency | F-BE-08b-02 | No
F-BE-08c-01 | Foundational | Brand Expression | Outdated content removal | Remove obsolete graphics | Audit all campus locations for obsolete graphics | Consultant | Single | No | Synergy | F-BE-08a-01 | Yes | Synergy candidate: same audit pass
F-BE-08c-02 | Foundational | Brand Expression | Outdated content removal | Remove obsolete graphics | Remove obsolete graphics | Third-party | Single | No | Synergy | F-BE-08a-03 | Yes | Synergy candidate: same removal mobilization
F-BE-08c-03 | Foundational | Brand Expression | Outdated content removal | Remove obsolete graphics | Quality control / punchwalk | Consultant | Single | No | Dependency | F-BE-08c-02 | No
F-BE-09a-01 | Foundational | Brand Expression | Baseline campus brand standards | Define minimum required branded moments for all buildings | Audit existing branded moments across all buildings | Consultant | Single | No | Synergy | F-BE-07a-01 | Yes | Synergy candidate: same brand audit pass
F-BE-09a-02 | Foundational | Brand Expression | Baseline campus brand standards | Define minimum required branded moments for all buildings | Define minimum baseline — Parallel A: identical minimums across all buildings | Consultant | Parallel A | No | Dependency | F-BE-09a-01 | No | Parallel track pending resolution with client
F-BE-09a-03 | Foundational | Brand Expression | Baseline campus brand standards | Define minimum required branded moments for all buildings | Define minimum baseline — Parallel B: tiered minimums by building type or prominence | Consultant | Parallel B | No | Dependency | F-BE-09a-01 | No | Parallel track pending resolution with client
F-BE-09a-04 | Foundational | Brand Expression | Baseline campus brand standards | Define minimum required branded moments for all buildings | Validate baseline definition with client and get approval | Consultant | Single | No | Dependency | F-BE-09a-02, F-BE-09a-03 | No | Parallel tracks converge here once decision is made
F-BE-09a-05 | Foundational | Brand Expression | Baseline campus brand standards | Define minimum required branded moments for all buildings | Document and distribute baseline standards | Consultant | Single | No | Dependency | F-BE-09a-04 | No | Cross-tier: prerequisite for all Intermediate brand expression work