## Task Database
Task ID | Tier | Category | Sub-heading | Source Sentence | Task | Lead | Track | Recommendation Only | Connection Type | Connected Task IDs | Connection Pending Confirmation | Notes
I-SW-10a-01 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create campus maps/directories that include accessible routes | Incorporate accessible route data from third-party audit into map content | Consultant | Single | No | Dependency | F-SW-04a-05 | No | Cannot proceed until accessible route documentation is complete
I-SW-10a-02 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create campus maps/directories that include accessible routes | Design campus map and directory layout | Consultant | Single | No | Dependency | F-SW-02a-05 | No | Nomenclature must be finalized before map content is set
I-SW-10a-03 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create campus maps/directories that include accessible routes | Fabrication | Third-party | Single | No | Synergy | I-SW-11a-03 | Yes | Synergy candidate: same fabrication run as building directories
I-SW-10a-04 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create campus maps/directories that include accessible routes | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-10a-03 | No
I-SW-10a-05 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create campus maps/directories that include accessible routes | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-10a-04 | No
I-SW-10b-01 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create building identification signage at key entrances | Define key entrance locations per building | Consultant | Single | No | Dependency | F-SW-06a-01 | No | Entrance audit informs this
I-SW-10b-02 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create building identification signage at key entrances | Design building identification signage per visual language and nomenclature | Consultant | Single | No | Dependency | F-SW-02a-05, F-SW-01c-02 | No
I-SW-10b-03 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create building identification signage at key entrances | Fabrication | Third-party | Single | No | Synergy | I-SW-10a-03 | Yes | Synergy candidate: same fabrication run
I-SW-10b-04 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create building identification signage at key entrances | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-10b-03 | No
I-SW-10b-05 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Create building identification signage at key entrances | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-10b-04 | No
I-SW-10c-01 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Improve visibility of existing building identification signage | Audit existing building ID signage for visibility issues (lighting, placement, obstruction) | Consultant | Single | No | Synergy | F-SW-06a-01 | Yes | Synergy candidate: same entrance audit pass
I-SW-10c-02 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Improve visibility of existing building identification signage | Define improvement interventions per location (lighting, repositioning, new install) | Consultant | Single | No | Dependency | I-SW-10c-01 | No
I-SW-10c-03 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Improve visibility of existing building identification signage | Coordinate improvements with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-10c-02 | No
I-SW-10c-04 | Intermediate | Signage and Wayfinding | Campus and building entry identification | Improve visibility of existing building identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-10c-03 | No
I-SW-11a-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create building directories | Define directory content per building using finalized nomenclature | Consultant | Single | No | Dependency | F-SW-02a-05 | No
I-SW-11a-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create building directories | Design directory format and layout | Consultant | Single | No | Dependency | I-SW-11a-01 | No
I-SW-11a-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create building directories | Fabrication | Third-party | Single | No | Synergy | I-SW-11b-02 | Yes | Synergy candidate: fabricate with elevator directories
I-SW-11a-04 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create building directories | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-11a-03 | No
I-SW-11a-05 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create building directories | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-11a-04 | No
I-SW-11b-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Place directories at elevators | Design elevator directory format (new fabrication) | Consultant | Single | No | Dependency | I-SW-11a-02 | No | New fabrication — not relocation
I-SW-11b-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Place directories at elevators | Fabrication | Third-party | Single | No | Synergy | I-SW-11a-03 | Yes | Synergy candidate: same fabrication run as building directories
I-SW-11b-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Place directories at elevators | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-11b-02 | No
I-SW-11b-04 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Place directories at elevators | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-11b-03 | No
I-SW-11c-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add floor information and amenities to directories | Compile floor information and amenity data per building | Consultant | Single | No | Dependency | F-SW-02a-05 | No
I-SW-11c-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add floor information and amenities to directories | Update directory design to include floor and amenity information | Consultant | Single | No | Dependency | I-SW-11a-02, I-SW-11c-01 | No
I-SW-11c-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add floor information and amenities to directories | Fabrication | Third-party | Single | No | Synergy | I-SW-11a-03 | Yes | Synergy candidate: same fabrication run
I-SW-11c-04 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add floor information and amenities to directories | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-11c-03 | No
I-SW-11c-05 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add floor information and amenities to directories | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-11c-04 | No
I-SW-11d-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create updatable directory templates | Define updatability requirements (frequency, who updates, format) | Consultant | Single | No | — |  | No
I-SW-11d-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create updatable directory templates | Design template system that allows content updates without full replacement | Consultant | Single | No | Dependency | I-SW-11a-02, I-SW-11d-01 | No | Cross-tier: feeds A-SW refresh and lifecycle management
I-SW-11d-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Create updatable directory templates | Document and hand off template system to client | Consultant | Single | No | Dependency | I-SW-11d-02 | No | Handoff to client for ongoing management
I-SW-11e-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Map all decision points across floor plates using audit data | Consultant | Single | No | Dependency | F-SW-02a-01 | No | Audit data from Foundational phase informs decision point mapping
I-SW-11e-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Identify placement gaps and conflicts | Consultant | Single | No | Dependency | I-SW-11e-01 | No
I-SW-11e-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Design corrected directional placement plan | Consultant | Single | No | Dependency | I-SW-11e-02 | No
I-SW-11e-04 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Remove existing misplaced directionals | Third-party | Single | No | — |  | No
I-SW-11e-05 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Fabrication | Third-party | Single | No | Synergy | I-SW-11f-03 | Yes | Synergy candidate: same fabrication run as deeper floor plate directionals
I-SW-11e-06 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-11e-05 | No
I-SW-11e-07 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Improve placement of directionals at decision points | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-11e-06 | No
I-SW-11f-01 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add directionals deeper into floor plates | Identify deep floor plate locations lacking directional coverage using audit data | Consultant | Single | No | Dependency | F-SW-02a-01 | No | Audit already complete — spatial gap-fill exercise
I-SW-11f-02 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add directionals deeper into floor plates | Design directional signage for deep floor plate locations | Consultant | Single | No | Dependency | I-SW-11f-01 | No
I-SW-11f-03 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add directionals deeper into floor plates | Fabrication | Third-party | Single | No | Synergy | I-SW-11e-05 | Yes | Synergy candidate: same fabrication run
I-SW-11f-04 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add directionals deeper into floor plates | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-11f-03 | No
I-SW-11f-05 | Intermediate | Signage and Wayfinding | Building directories and interior directionals | Add directionals deeper into floor plates | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-11f-04 | No
I-SW-12a-01 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Audit existing bike parking signage for visibility and placement issues | Consultant | Single | No | — |  | No | TBD depth of intervention — pending clarification
I-SW-12a-02 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Define interventions per location (lighting, repositioning, new install) | Consultant | Single | No | Dependency | I-SW-12a-01 | No
I-SW-12a-03 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Remove existing inadequate signage | Third-party | Single | No | — |  | No
I-SW-12a-04 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Fabrication | Third-party | Single | No | Synergy | I-SW-12b-03, I-SW-12c-03, I-SW-12d-04 | Yes | Synergy candidate: amenity signage fabrication run
I-SW-12a-05 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-12a-04 | No
I-SW-12a-06 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of bike parking identification | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-12a-05 | No
I-SW-12b-01 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Create missing signage for employee services (e.g. printers) | Inventory all employee service locations lacking signage | Consultant | Single | No | — |  | No
I-SW-12b-02 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Create missing signage for employee services (e.g. printers) | Design employee service identification signage | Consultant | Single | No | Dependency | I-SW-12b-01 | No
I-SW-12b-03 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Create missing signage for employee services (e.g. printers) | Fabrication | Third-party | Single | No | Synergy | I-SW-12a-04 | Yes | Synergy candidate: same amenity fabrication run
I-SW-12b-04 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Create missing signage for employee services (e.g. printers) | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-12b-03 | No
I-SW-12b-05 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Create missing signage for employee services (e.g. printers) | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-12b-04 | No
I-SW-12c-01 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of restroom identification | Audit existing restroom signage for visibility and placement issues | Consultant | Single | No | Synergy | I-SW-12a-01 | Yes | Synergy candidate: same amenity audit pass
I-SW-12c-02 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of restroom identification | Define interventions per location (lighting, repositioning, new install) | Consultant | Single | No | Dependency | I-SW-12c-01 | No
I-SW-12c-03 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of restroom identification | Fabrication | Third-party | Single | No | Synergy | I-SW-12a-04 | Yes | Synergy candidate: same amenity fabrication run
I-SW-12c-04 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of restroom identification | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-12c-03 | No
I-SW-12c-05 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Improve visibility and placement of restroom identification | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-12c-04 | No
I-SW-12d-01 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Audit existing signage to determine scope per location (cosmetic refresh vs. replacement) | Consultant | Single | No | — |  | No | Depth of intervention varies by location — audit determines which
I-SW-12d-02 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Design updated signage per location scope | Consultant | Single | No | Dependency | I-SW-12d-01 | No
I-SW-12d-03 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Remove existing signage where full replacement is required | Third-party | Single | No | Dependency | I-SW-12d-01 | No
I-SW-12d-04 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Fabrication | Third-party | Single | No | Synergy | I-SW-12a-04 | Yes | Synergy candidate: amenity fabrication run
I-SW-12d-05 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-12d-04 | No
I-SW-12d-06 | Intermediate | Signage and Wayfinding | Amenity and support space identification | Update café and cafeteria signage and wayfinding | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-12d-05 | No
I-SW-13a-01 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Improve visibility and placement of zone/neighborhood identifications | Audit existing zone/neighborhood identification for visibility and placement issues | Consultant | Single | No | Dependency | F-SW-02a-05 | No | Nomenclature must be finalized before zone IDs are assessed
I-SW-13a-02 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Improve visibility and placement of zone/neighborhood identifications | Define interventions (lighting, repositioning, new install) per location | Consultant | Single | No | Dependency | I-SW-13a-01 | No
I-SW-13a-03 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Improve visibility and placement of zone/neighborhood identifications | Fabrication | Third-party | Single | No | Synergy | I-SW-13b-02, I-SW-13c-02 | Yes | Synergy candidate: space ID fabrication run
I-SW-13a-04 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Improve visibility and placement of zone/neighborhood identifications | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-13a-03 | No
I-SW-13a-05 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Improve visibility and placement of zone/neighborhood identifications | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-13a-04 | No
I-SW-13b-01 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create workstation identification signage | Define workstation ID format per nomenclature framework | Consultant | Single | No | Dependency | F-SW-02a-05 | No
I-SW-13b-02 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create workstation identification signage | Fabrication | Third-party | Single | No | Synergy | I-SW-13a-03 | Yes | Synergy candidate: same space ID fabrication run
I-SW-13b-03 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create workstation identification signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-13b-02 | No
I-SW-13b-04 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create workstation identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-13b-03 | No
I-SW-13c-01 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create flex space identification signage | Define flex space ID format and content requirements | Consultant | Single | No | Dependency | F-SW-02a-05 | No
I-SW-13c-02 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create flex space identification signage | Fabrication | Third-party | Single | No | Synergy | I-SW-13a-03 | Yes | Synergy candidate: same space ID fabrication run
I-SW-13c-03 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create flex space identification signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-13c-02 | No
I-SW-13c-04 | Intermediate | Signage and Wayfinding | Space, zone, and workstation identification | Create flex space identification signage | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-13c-03 | No
I-SW-14a-01 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage on routes from parking to reception(s) | Map visitor routes from all parking areas to each reception point | Consultant | Single | No | Dependency | F-SW-05a-02, F-SW-06a-01 | No | Parking and entrance work must be resolved first
I-SW-14a-02 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage on routes from parking to reception(s) | Design directional signage for visitor routes | Consultant | Single | No | Dependency | I-SW-14a-01 | No
I-SW-14a-03 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage on routes from parking to reception(s) | Fabrication | Third-party | Single | No | Synergy | I-SW-14b-02, I-SW-14c-03, I-SW-14d-04 | Yes | Synergy candidate: visitor journey fabrication run
I-SW-14a-04 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage on routes from parking to reception(s) | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-14a-03 | No
I-SW-14a-05 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage on routes from parking to reception(s) | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-14a-04 | No
I-SW-14b-01 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage along routes from drop-off points to reception(s) | Map routes from all designated drop-off points to reception | Consultant | Single | No | Dependency | F-SW-06d-01 | No | Drop-off zones must be designated first
I-SW-14b-02 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage along routes from drop-off points to reception(s) | Fabrication | Third-party | Single | No | Synergy | I-SW-14a-03 | Yes | Synergy candidate: visitor journey fabrication run
I-SW-14b-03 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage along routes from drop-off points to reception(s) | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-14b-02 | No
I-SW-14b-04 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create signage along routes from drop-off points to reception(s) | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-14b-03 | No
I-SW-14c-01 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create visitor navigation signage | Define all visitor navigation touchpoints across campus | Consultant | Single | No | Dependency | I-SW-14a-01, I-SW-14b-01 | No
I-SW-14c-02 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create visitor navigation signage | Design visitor navigation signage system | Consultant | Single | No | Dependency | I-SW-14c-01 | No
I-SW-14c-03 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create visitor navigation signage | Fabrication | Third-party | Single | No | Synergy | I-SW-14a-03 | Yes | Synergy candidate: visitor journey fabrication run
I-SW-14c-04 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create visitor navigation signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-14c-03 | No
I-SW-14c-05 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Create visitor navigation signage | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-14c-04 | No
I-SW-14d-01 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Identify who currently owns and maintains the PDF arrival instructions | Consultant | Single | No | — |  | No | PDF owner must be looped in before any physical replacement occurs
I-SW-14d-02 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Map all information currently conveyed in PDFs to physical wayfinding touchpoints | Consultant | Single | No | Dependency | I-SW-14d-01 | No
I-SW-14d-03 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Design permanent in situ wayfinding to replace PDF content | Consultant | Single | No | Dependency | I-SW-14d-02 | No
I-SW-14d-04 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Fabrication | Third-party | Single | No | Synergy | I-SW-14a-03 | Yes | Synergy candidate: visitor journey fabrication run
I-SW-14d-05 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-14d-04 | No
I-SW-14d-06 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Retire PDF instructions — brief PDF owner on transition | Consultant | Single | No | Dependency | I-SW-14d-05 | No | Handoff to PDF owner to retire document
I-SW-14d-07 | Intermediate | Signage and Wayfinding | Visitor journey navigation | Replace PDF arrival instructions with permanent wayfinding in situ | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-14d-05 | No
I-SW-15a-01 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Audit all garage signage for color contrast issues | Consultant | Single | No | Dependency | F-SW-05a-01 | No | Builds on Foundational garage audit
I-SW-15a-02 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Define updated color standards for garage signage | Consultant | Single | No | Dependency | I-SW-15a-01 | No
I-SW-15a-03 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Remove existing low-contrast signage | Third-party | Single | No | — |  | No
I-SW-15a-04 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Fabrication | Third-party | Single | No | Synergy | I-SW-15b-03 | Yes | Synergy candidate: outdoor/parking fabrication run
I-SW-15a-05 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-15a-04 | No
I-SW-15a-06 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Improve color contrast on all garage signage | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-15a-05 | No
I-SW-15b-01 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Create signage on shared pedestrian, cyclist, and vehicular routes | Map all shared routes across campus | Consultant | Single | No | Dependency | F-SW-04a-05 | No | Accessible route documentation informs this
I-SW-15b-02 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Create signage on shared pedestrian, cyclist, and vehicular routes | Design shared route signage | Consultant | Single | No | Dependency | I-SW-15b-01 | No
I-SW-15b-03 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Create signage on shared pedestrian, cyclist, and vehicular routes | Fabrication | Third-party | Single | No | Synergy | I-SW-15a-04 | Yes | Synergy candidate: outdoor/parking fabrication run
I-SW-15b-04 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Create signage on shared pedestrian, cyclist, and vehicular routes | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-SW-15b-03 | No
I-SW-15b-05 | Intermediate | Signage and Wayfinding | Parking and outdoor navigation | Create signage on shared pedestrian, cyclist, and vehicular routes | Quality control / punchwalk | Consultant | Single | No | Dependency | I-SW-15b-04 | No