## Task Database
Task ID | Tier | Category | Sub-heading | Source Sentence | Task | Lead | Track | Recommendation Only | Connection Type | Connected Task IDs | Connection Pending Confirmation | Notes
I-BE-16a-01 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create an evergreen content program | Define what constitutes evergreen content per brand category guidelines | Consultant | Single | No | Dependency | F-BE-07a-02 | No | Brand categories must be defined first
I-BE-16a-02 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create an evergreen content program | Develop evergreen content program framework (themes, formats, locations) | Consultant | Single | No | Dependency | I-BE-16a-01 | No | Cross-tier: feeds A-BE content refresh and lifecycle tasks
I-BE-16a-03 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create an evergreen content program | Design and produce initial evergreen content | Consultant | Single | No | Dependency | I-BE-16a-02 | No
I-BE-16a-04 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create an evergreen content program | Fabrication and installation | Third-party | Single | No | — |  | No
I-BE-16a-05 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create an evergreen content program | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-16a-04 | No
I-BE-16b-01 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create a seasonal content program | Define what constitutes seasonal content and establish refresh calendar | Consultant | Single | No | Dependency | F-BE-07a-02 | No | Cross-tier: feeds A-BE seasonal refresh cycles
I-BE-16b-02 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create a seasonal content program | Develop seasonal content program framework | Consultant | Single | No | Dependency | I-BE-16b-01 | No
I-BE-16b-03 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create a seasonal content program | Design and produce first seasonal content cycle | Consultant | Single | No | Dependency | I-BE-16b-02 | No
I-BE-16b-04 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create a seasonal content program | Fabrication and installation | Third-party | Single | No | Synergy | I-BE-16a-04 | Yes | Synergy candidate: first seasonal and evergreen install in same mobilization
I-BE-16b-05 | Intermediate | Brand Expression | Evergreen vs. seasonal workplace content | Create a seasonal content program | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-16b-04 | No
I-BE-17a-01 | Intermediate | Brand Expression | Brand storytelling and product display | Create strategy for storytelling in corridors, circulation zones, common spaces, and outdoor spaces | Define storytelling zones and content hierarchy across campus | Consultant | Single | No | Dependency | F-BE-07a-02, F-BE-09a-05 | No | Brand categories and baseline standards must be established
I-BE-17a-02 | Intermediate | Brand Expression | Brand storytelling and product display | Create strategy for storytelling in corridors, circulation zones, common spaces, and outdoor spaces | Develop storytelling strategy document | Consultant | Single | No | Dependency | I-BE-17a-01 | No
I-BE-17a-03 | Intermediate | Brand Expression | Brand storytelling and product display | Create strategy for storytelling in corridors, circulation zones, common spaces, and outdoor spaces | Validate strategy with client stakeholders | Consultant | Single | No | Dependency | I-BE-17a-02 | No
I-BE-17b-01 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Define modular display requirements per space type and product category | Consultant | Single | No | Dependency | F-BE-07d-02 | No | Product display guidelines must be defined first
I-BE-17b-02 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Design modular display system | Consultant | Single | No | Dependency | I-BE-17b-01 | No
I-BE-17b-03 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Remove existing non-modular or outdated display systems | Third-party | Single | No | Synergy | F-BE-08a-03 | Yes | Synergy candidate: removal mobilization
I-BE-17b-04 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Fabrication | Third-party | Single | No | — |  | No
I-BE-17b-05 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-17b-04 | No
I-BE-17b-06 | Intermediate | Brand Expression | Brand storytelling and product display | Create modular product display systems | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-17b-05 | No
I-BE-17c-01 | Intermediate | Brand Expression | Brand storytelling and product display | Consider reusable product displays | Benchmark existing reusable display solutions in market | Consultant | Single | No | Synergy | I-BE-17b-01 | Yes | Synergy candidate: informs modular display design — run concurrently
I-BE-17c-02 | Intermediate | Brand Expression | Brand storytelling and product display | Consider reusable product displays | Conduct vendor outreach for reusable display options | Consultant | Single | No | Dependency | I-BE-17c-01 | No
I-BE-17c-03 | Intermediate | Brand Expression | Brand storytelling and product display | Consider reusable product displays | Evaluate feasibility and present recommendation to client | Consultant | Single | No | Dependency | I-BE-17c-02 | No
I-BE-17c-04 | Intermediate | Brand Expression | Brand storytelling and product display | Consider reusable product displays | Design reusable display system in-house if no suitable vendor solution exists | Consultant | Single | No | Dependency | I-BE-17c-03 | No | Conditional — only if vendor route is not viable
I-BE-17d-01 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Identify locations appropriate for history and innovation storytelling | Consultant | Single | No | Dependency | I-BE-17a-02 | No | Storytelling strategy must be defined first
I-BE-17d-02 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Develop content brief for history and innovation stories | Consultant | Single | No | Dependency | I-BE-17d-01 | No
I-BE-17d-03 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Design physical storytelling installations | Consultant | Single | No | Dependency | I-BE-17d-02 | No
I-BE-17d-04 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Fabrication | Third-party | Single | No | — |  | No
I-BE-17d-05 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-17d-04 | No
I-BE-17d-06 | Intermediate | Brand Expression | Brand storytelling and product display | Create opportunities for storytelling of history and innovation stories | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-17d-05 | No
I-BE-18a-01 | Intermediate | Brand Expression | Art and cultural programs | Create a strategy for inviting local and regional art that is culturally relevant | Define curatorial criteria for culturally relevant local and regional art | Consultant | Single | No | Dependency | F-BE-07c-02 | No | Art use guidelines must be defined first
I-BE-18a-02 | Intermediate | Brand Expression | Art and cultural programs | Create a strategy for inviting local and regional art that is culturally relevant | Develop art invitation and curation strategy | Consultant | Single | No | Dependency | I-BE-18a-01 | No
I-BE-18a-03 | Intermediate | Brand Expression | Art and cultural programs | Create a strategy for inviting local and regional art that is culturally relevant | Validate strategy with client and relevant community stakeholders | Consultant | Single | No | Dependency | I-BE-18a-02 | No
I-BE-18b-01 | Intermediate | Brand Expression | Art and cultural programs | Create rotating art displays | Define rotation schedule and display locations | Consultant | Single | No | Dependency | I-BE-18a-02 | No
I-BE-18b-02 | Intermediate | Brand Expression | Art and cultural programs | Create rotating art displays | Design display infrastructure to support rotation | Consultant | Single | No | Dependency | I-BE-18b-01 | No
I-BE-18b-03 | Intermediate | Brand Expression | Art and cultural programs | Create rotating art displays | Fabrication and installation of display infrastructure | Third-party | Single | No | — |  | No
I-BE-18b-04 | Intermediate | Brand Expression | Art and cultural programs | Create rotating art displays | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-18b-03 | No
I-BE-18c-01 | Intermediate | Brand Expression | Art and cultural programs | Create opportunities for co-creation with volunteer employees | Define co-creation program scope, eligibility, and submission process | Consultant | Single | No | Dependency | I-BE-18a-02 | No | Art strategy must be in place
I-BE-18c-02 | Intermediate | Brand Expression | Art and cultural programs | Create opportunities for co-creation with volunteer employees | Coordinate with HR and facilities on program logistics and space allocation | Consultant | Single | No | Dependency | I-BE-18c-01 | No
I-BE-18c-03 | Intermediate | Brand Expression | Art and cultural programs | Create opportunities for co-creation with volunteer employees | Launch program and collect submissions | Client | Single | No | Dependency | I-BE-18c-02 | No | Client-led after program design is handed off
I-BE-18c-04 | Intermediate | Brand Expression | Art and cultural programs | Create opportunities for co-creation with volunteer employees | Install selected co-created works | Third-party | Single | No | — |  | No
I-BE-19a-01 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Identify key arrival touchpoints across campus for branded moment placement | Consultant | Single | No | Dependency | F-SW-06a-01, F-BE-09a-05 | No | Entrance audit and baseline brand standards must be complete
I-BE-19a-02 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Design branded welcome moment installations per location | Consultant | Single | No | Dependency | I-BE-19a-01 | No
I-BE-19a-03 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Remove existing outdated or unbranded arrival elements | Third-party | Single | No | Synergy | F-BE-08a-03 | Yes | Synergy candidate: removal mobilization
I-BE-19a-04 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Fabrication | Third-party | Single | No | — |  | No
I-BE-19a-05 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-19a-04 | No
I-BE-19a-06 | Intermediate | Brand Expression | Arrival experience upgrades | Create branded welcome moments | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-19a-05 | No
I-BE-19b-01 | Intermediate | Brand Expression | Arrival experience upgrades | Create visitor photo moments | Identify locations appropriate for visitor photo moments | Consultant | Single | No | Dependency | I-BE-19a-01 | No
I-BE-19b-02 | Intermediate | Brand Expression | Arrival experience upgrades | Create visitor photo moments | Design visitor photo moment installations | Consultant | Single | No | Dependency | I-BE-19b-01 | No
I-BE-19b-03 | Intermediate | Brand Expression | Arrival experience upgrades | Create visitor photo moments | Fabrication | Third-party | Single | No | Synergy | I-BE-19a-04 | Yes | Synergy candidate: same arrival experience fabrication run
I-BE-19b-04 | Intermediate | Brand Expression | Arrival experience upgrades | Create visitor photo moments | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-19b-03 | No
I-BE-19b-05 | Intermediate | Brand Expression | Arrival experience upgrades | Create visitor photo moments | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-19b-04 | No
I-BE-20a-01 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Audit elevators, secondary circulation, and smaller shared spaces for branded moment visibility issues | Consultant | Single | No | Dependency | F-BE-09a-05 | No | Baseline brand standards must be established first
I-BE-20a-02 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Define interventions per location: lighting improvements | Consultant | Single | No | Dependency | I-BE-20a-01 | No | Three parallel intervention types — lighting, repositioning, new install
I-BE-20a-03 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Define interventions per location: repositioning of existing branded elements | Consultant | Single | No | Dependency | I-BE-20a-01 | No
I-BE-20a-04 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Define interventions per location: new branded installations | Consultant | Single | No | Dependency | I-BE-20a-01 | No
I-BE-20a-05 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Fabrication of new branded elements | Third-party | Single | No | — |  | No
I-BE-20a-06 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-20a-05 | No
I-BE-20a-07 | Intermediate | Brand Expression | Overlooked touchpoints | Improve visibility of branded moments in elevators, secondary circulation spaces, and in smaller shared spaces | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-20a-06 | No
I-BE-21a-01 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Audit all workspaces and meeting rooms for branded moment presence and quality | Consultant | Single | No | Dependency | F-BE-09a-05 | No
I-BE-21a-02 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Define improvement and creation scope per room type | Consultant | Single | No | Dependency | I-BE-21a-01 | No
I-BE-21a-03 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Design branded moment installations for workspaces and meeting rooms | Consultant | Single | No | Dependency | I-BE-21a-02 | No
I-BE-21a-04 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Remove existing outdated branded elements | Third-party | Single | No | Synergy | F-BE-08a-03 | Yes | Synergy candidate: removal mobilization
I-BE-21a-05 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Fabrication | Third-party | Single | No | — |  | No
I-BE-21a-06 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Coordinate installation with fabricator, installer, and facilities | Consultant | Single | No | Dependency | I-BE-21a-05 | No
I-BE-21a-07 | Intermediate | Brand Expression | Workspace and meeting room identity | Create and improve existing branded moments in workspaces and meeting rooms | Quality control / punchwalk | Consultant | Single | No | Dependency | I-BE-21a-06 | No