## Task Database
Task ID | Tier | Category | Sub-heading | Source Sentence | Task | Lead | Track | Recommendation Only | Connection Type | Connected Task IDs | Connection Pending Confirmation | Notes
A-SW-22a-01 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create workplace wayfinding guidelines | Synthesize all Foundational and Intermediate wayfinding decisions into unified guidelines document | Consultant | Single | No | Dependency | F-SW-02a-05, I-SW-11d-02 | No | Cross-tier: requires all prior wayfinding work to be substantially complete
A-SW-22a-02 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create workplace wayfinding guidelines | Define guidelines by space type | Consultant | Single | No | Dependency | A-SW-22a-01 | No
A-SW-22a-03 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create workplace wayfinding guidelines | Validate with client and distribute | Consultant | Single | No | Dependency | A-SW-22a-02 | No
A-SW-22b-01 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create signage standards | Compile all signage design decisions from Foundational and Intermediate phases | Consultant | Single | No | Dependency | F-SW-01c-02 | No | Design direction from F-SW-01c-02 is the primary input
A-SW-22b-02 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create signage standards | Draft sign standards manual covering type, size, materials, placement, and content rules | Consultant | Single | No | Dependency | A-SW-22b-01 | No
A-SW-22b-03 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Create signage standards | Validate and distribute sign standards manual | Consultant | Single | No | Dependency | A-SW-22b-02 | No
A-SW-22c-01 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Define standards by space type | Map all space types across campus | Consultant | Single | No | Dependency | F-SW-02a-05 | No
A-SW-22c-02 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Define standards by space type | Define signage and wayfinding standards for each space type | Consultant | Single | No | Dependency | A-SW-22b-02, A-SW-22c-01 | No
A-SW-22c-03 | Advanced | Signage and Wayfinding | Workplace standards and guidelines | Define standards by space type | Document and distribute | Consultant | Single | No | Dependency | A-SW-22c-02 | No
A-SW-23a-01 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create signage request processes | Define what types of signage require a formal request process | Consultant | Single | No | Dependency | A-SW-22b-03 | No | Standards must be published before request process is designed
A-SW-23a-02 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create signage request processes | Design signage request workflow | Consultant | Single | No | Dependency | A-SW-23a-01 | No
A-SW-23a-03 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create signage request processes | Document and distribute request process to relevant stakeholders | Consultant | Single | No | Dependency | A-SW-23a-02 | No | Handoff to client for ongoing operation
A-SW-23b-01 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create approval workflows | Identify approval authorities for new signage, wayfinding, and brand (TBD on org chart) | Consultant | Single | No | Dependency | A-SW-23a-02 | No
A-SW-23b-02 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create approval workflows | Design approval workflow for each signage type | Consultant | Single | No | Dependency | A-SW-23b-01 | No
A-SW-23b-03 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Create approval workflows | Document and distribute approval workflows | Consultant | Single | No | Dependency | A-SW-23b-02 | No
A-SW-23c-01 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Define ownership roles | Map existing org structure to identify candidate owners for signage and wayfinding | Consultant | Single | No | — |  | No | TBD — depends on client org chart
A-SW-23c-02 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Define ownership roles | Define ownership roles and responsibilities | Consultant | Single | No | Dependency | A-SW-23c-01 | No
A-SW-23c-03 | Advanced | Signage and Wayfinding | Request, approval, and governance systems | Define ownership roles | Formalize and communicate roles to relevant teams | Consultant | Single | No | Dependency | A-SW-23c-02 | No | Handoff to client for ongoing governance
A-SW-24a-01 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create signage refresh processes | Define refresh triggers (time-based, condition-based, change-driven) | Consultant | Single | No | Dependency | A-SW-22b-03 | No
A-SW-24a-02 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create signage refresh processes | Design refresh process and timeline | Consultant | Single | No | Dependency | A-SW-24a-01 | No
A-SW-24a-03 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create signage refresh processes | Document and hand off to client | Consultant | Single | No | Dependency | A-SW-24a-02 | No
A-SW-24b-01 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create replacement standards | Define criteria for when signage is repaired vs. replaced | Consultant | Single | No | Dependency | A-SW-22b-03 | No
A-SW-24b-02 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create replacement standards | Document replacement standards | Consultant | Single | No | Dependency | A-SW-24b-01 | No
A-SW-24b-03 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create replacement standards | Hand off to client | Consultant | Single | No | Dependency | A-SW-24b-02 | No
A-SW-24c-01 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create decommissioning standards | Define criteria and process for decommissioning signage | Consultant | Single | No | — |  | No
A-SW-24c-02 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create decommissioning standards | Document decommissioning standards | Consultant | Single | No | Dependency | A-SW-24c-01 | No
A-SW-24c-03 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create decommissioning standards | Hand off to client | Consultant | Single | No | Dependency | A-SW-24c-02 | No
A-SW-24d-01 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create asset lifecycle procedures | Define full lifecycle stages for all signage asset types | Consultant | Single | No | Dependency | A-SW-24a-01, A-SW-24b-01, A-SW-24c-01 | No | Synthesizes refresh, replacement, and decommissioning into unified lifecycle
A-SW-24d-02 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create asset lifecycle procedures | Document asset lifecycle procedures | Consultant | Single | No | Dependency | A-SW-24d-01 | No
A-SW-24d-03 | Advanced | Signage and Wayfinding | Refresh and lifecycle management | Create asset lifecycle procedures | Hand off to client | Consultant | Single | No | Dependency | A-SW-24d-02 | No
A-SW-25a-01 | Advanced | Signage and Wayfinding | Integrated digital navigation | Connect booking tools with signage naming systems | Define requirements for naming alignment between physical signage and booking tools | Consultant | Single | No | Dependency | F-SW-02a-05, A-SW-22b-03 | No | Handoff point — IT leads implementation
A-SW-25a-02 | Advanced | Signage and Wayfinding | Integrated digital navigation | Connect booking tools with signage naming systems | Brief IT on integration requirements and transfer responsibility | Consultant | Single | No | Dependency | A-SW-25a-01 | No
A-SW-25a-03 | Advanced | Signage and Wayfinding | Integrated digital navigation | Connect booking tools with signage naming systems | IT implements booking tool and signage naming integration | Client / IT | Single | Yes | Dependency | A-SW-25a-02 | No | Recommendation — client/IT led; listed to show full complexity
A-SW-25b-01 | Advanced | Signage and Wayfinding | Integrated digital navigation | Integrate digital directories with physical systems | Define requirements for digital/physical directory integration | Consultant | Single | No | Dependency | I-SW-11a-02 | No
A-SW-25b-02 | Advanced | Signage and Wayfinding | Integrated digital navigation | Integrate digital directories with physical systems | Brief IT on integration requirements and transfer responsibility | Consultant | Single | No | Dependency | A-SW-25b-01 | No | Handoff to IT
A-SW-25b-03 | Advanced | Signage and Wayfinding | Integrated digital navigation | Integrate digital directories with physical systems | IT implements integration | Client / IT | Single | Yes | Dependency | A-SW-25b-02 | No | Recommendation — client/IT led
A-SW-25c-01 | Advanced | Signage and Wayfinding | Integrated digital navigation | Synchronize naming across platforms | Inventory all platforms where campus names appear (booking, maps, intranet, directories, signage) | Consultant | Single | No | Dependency | F-SW-02a-05 | No
A-SW-25c-02 | Advanced | Signage and Wayfinding | Integrated digital navigation | Synchronize naming across platforms | Define cross-platform naming governance and data ownership | Consultant | Single | No | Dependency | A-SW-25c-01, A-SW-23c-02 | No
A-SW-25c-03 | Advanced | Signage and Wayfinding | Integrated digital navigation | Synchronize naming across platforms | Brief relevant platform owners and transfer responsibility | Consultant | Single | No | Dependency | A-SW-25c-02 | No | Handoff — client/IT leads synchronization
A-SW-25c-04 | Advanced | Signage and Wayfinding | Integrated digital navigation | Synchronize naming across platforms | Client/IT implements platform synchronization | Client / IT | Single | Yes | Dependency | A-SW-25c-03 | No | Recommendation — client/IT led
A-SW-26a-01 | Advanced | Signage and Wayfinding | Measurement and feedback | Create navigation benchmarks | Define what navigation success looks like (metrics, KPIs) | Consultant | Single | No | — |  | No
A-SW-26a-02 | Advanced | Signage and Wayfinding | Measurement and feedback | Create navigation benchmarks | Establish baseline benchmarks using pre-implementation data | Consultant | Single | No | Dependency | A-SW-26a-01 | No
A-SW-26a-03 | Advanced | Signage and Wayfinding | Measurement and feedback | Create navigation benchmarks | Document and hand off benchmark framework to client | Consultant | Single | No | Dependency | A-SW-26a-02 | No
A-SW-26b-01 | Advanced | Signage and Wayfinding | Measurement and feedback | Create visitor success metrics | Define visitor journey success metrics | Consultant | Single | No | Dependency | I-SW-14c-01 | No | Visitor journey must be designed first
A-SW-26b-02 | Advanced | Signage and Wayfinding | Measurement and feedback | Create visitor success metrics | Design data collection method for visitor metrics | Consultant | Single | No | Dependency | A-SW-26b-01 | No
A-SW-26b-03 | Advanced | Signage and Wayfinding | Measurement and feedback | Create visitor success metrics | Hand off to client for implementation | Consultant | Single | No | Dependency | A-SW-26b-02 | No
A-SW-26c-01 | Advanced | Signage and Wayfinding | Measurement and feedback | Create employee feedback systems | Define feedback channels and frequency for employee wayfinding experience | Consultant | Single | No | — |  | No
A-SW-26c-02 | Advanced | Signage and Wayfinding | Measurement and feedback | Create employee feedback systems | Design feedback system (tool recommendation or manual workflow — TBD) | Consultant | Single | No | Dependency | A-SW-26c-01 | No | Tool vs. manual workflow TBD — depends on client resources
A-SW-26c-03 | Advanced | Signage and Wayfinding | Measurement and feedback | Create employee feedback systems | Hand off to client for implementation and ongoing management | Consultant | Single | No | Dependency | A-SW-26c-02 | No | TBD who owns post-handoff
A-SW-26d-01 | Advanced | Signage and Wayfinding | Measurement and feedback | Create issue tracking processes | Define what constitutes a reportable signage/wayfinding issue | Consultant | Single | No | — |  | No
A-SW-26d-02 | Advanced | Signage and Wayfinding | Measurement and feedback | Create issue tracking processes | Design issue tracking process (software tool or manual workflow — TBD) | Consultant | Single | No | Dependency | A-SW-26d-01 | No | Tool vs. manual TBD — ownership TBD post-handoff
A-SW-26d-03 | Advanced | Signage and Wayfinding | Measurement and feedback | Create issue tracking processes | Hand off to client for implementation | Consultant | Single | No | Dependency | A-SW-26d-02 | No
A-BE-27a-01 | Advanced | Brand Expression | Workplace brand standards and guidelines | Create workplace brand experience guidelines | Synthesize all brand decisions from Foundational and Intermediate phases | Consultant | Single | No | Dependency | F-BE-07a-02, F-BE-09a-05, I-BE-17a-02 | No | Cross-tier: requires all prior brand work to be substantially complete
A-BE-27a-02 | Advanced | Brand Expression | Workplace brand standards and guidelines | Create workplace brand experience guidelines | Draft brand experience guidelines document | Consultant | Single | No | Dependency | A-BE-27a-01 | No
A-BE-27a-03 | Advanced | Brand Expression | Workplace brand standards and guidelines | Create workplace brand experience guidelines | Validate and distribute to client | Consultant | Single | No | Dependency | A-BE-27a-02 | No
A-BE-27b-01 | Advanced | Brand Expression | Workplace brand standards and guidelines | Define brand standards by space type | Map all space types to brand category framework | Consultant | Single | No | Dependency | F-BE-07a-02 | No
A-BE-27b-02 | Advanced | Brand Expression | Workplace brand standards and guidelines | Define brand standards by space type | Define brand standards for each space type | Consultant | Single | No | Dependency | A-BE-27a-02, A-BE-27b-01 | No
A-BE-27b-03 | Advanced | Brand Expression | Workplace brand standards and guidelines | Define brand standards by space type | Document and distribute | Consultant | Single | No | Dependency | A-BE-27b-02 | No
A-BE-28a-01 | Advanced | Brand Expression | Governance and ownership systems | Create brand governance processes | Identify brand governance authority on org chart (TBD) | Consultant | Single | No | — |  | No
A-BE-28a-02 | Advanced | Brand Expression | Governance and ownership systems | Create brand governance processes | Design brand governance process for new and updated brand expressions | Consultant | Single | No | Dependency | A-BE-28a-01 | No
A-BE-28a-03 | Advanced | Brand Expression | Governance and ownership systems | Create brand governance processes | Document and distribute governance process | Consultant | Single | No | Dependency | A-BE-28a-02 | No | Handoff to client for ongoing governance
A-BE-28b-01 | Advanced | Brand Expression | Governance and ownership systems | Define ownership across teams | Map brand touchpoints to responsible teams | Consultant | Single | No | Dependency | A-BE-28a-01 | No
A-BE-28b-02 | Advanced | Brand Expression | Governance and ownership systems | Define ownership across teams | Define ownership roles and responsibilities per touchpoint | Consultant | Single | No | Dependency | A-BE-28b-01 | No
A-BE-28b-03 | Advanced | Brand Expression | Governance and ownership systems | Define ownership across teams | Communicate and formalize with relevant teams | Consultant | Single | No | Dependency | A-BE-28b-02 | No
A-BE-28c-01 | Advanced | Brand Expression | Governance and ownership systems | Create approval workflows | Define approval requirements for new signage, wayfinding, and brand expressions | Consultant | Single | No | Dependency | A-BE-28a-02 | No
A-BE-28c-02 | Advanced | Brand Expression | Governance and ownership systems | Create approval workflows | Design approval workflow per expression type | Consultant | Single | No | Dependency | A-BE-28c-01 | No
A-BE-28c-03 | Advanced | Brand Expression | Governance and ownership systems | Create approval workflows | Document and hand off to client | Consultant | Single | No | Dependency | A-BE-28c-02 | No
A-BE-29a-01 | Advanced | Brand Expression | Centralize asset management | Create a centralized brand asset library | Define scope and structure of asset library (file types, naming conventions, access levels) | Consultant | Single | No | Dependency | A-BE-27a-03 | No | Brand guidelines must be published first
A-BE-29a-02 | Advanced | Brand Expression | Centralize asset management | Create a centralized brand asset library | Identify need for third-party or internal platform for hosting | Consultant | Single | No | Dependency | A-BE-29a-01 | No
A-BE-29a-03 | Advanced | Brand Expression | Centralize asset management | Create a centralized brand asset library | Select or brief platform, populate with assets, and hand off to client | Consultant | Single | No | Dependency | A-BE-29a-02 | No | Handoff to client for ongoing management
A-BE-29b-01 | Advanced | Brand Expression | Centralize asset management | Define what constitutes evergreen assets and seasonal assets | Consultant-led definition of evergreen vs. seasonal asset criteria | Consultant | Parallel A | No | Dependency | I-BE-16a-02, I-BE-16b-01 | No | Parallel track — both consultant and adidas brand/marketing input required
A-BE-29b-02 | Advanced | Brand Expression | Centralize asset management | Define what constitutes evergreen assets and seasonal assets | adidas brand/marketing input on evergreen vs. seasonal criteria | Client | Parallel B | No | Dependency | I-BE-16a-02, I-BE-16b-01 | No | Parallel track — both tracks must be synthesized before definition is finalized
A-BE-29b-03 | Advanced | Brand Expression | Centralize asset management | Define what constitutes evergreen assets and seasonal assets | Synthesize inputs and finalize definition | Consultant | Single | No | Dependency | A-BE-29b-01, A-BE-29b-02 | No | Parallel tracks converge here
A-BE-29c-01 | Advanced | Brand Expression | Centralize asset management | Create templates and reusable files | Define template needs per asset and expression type | Consultant | Single | No | Dependency | A-BE-27a-03 | No
A-BE-29c-02 | Advanced | Brand Expression | Centralize asset management | Create templates and reusable files | Design and produce templates | Consultant | Single | No | Dependency | A-BE-29c-01 | No
A-BE-29c-03 | Advanced | Brand Expression | Centralize asset management | Create templates and reusable files | Upload to asset library and hand off to client | Consultant | Single | No | Dependency | A-BE-29a-03, A-BE-29c-02 | No | Asset library must exist before templates are uploaded
A-BE-30a-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create annual review cycles | Define scope and frequency of annual brand content review | Consultant | Single | No | Dependency | A-BE-27a-03 | No
A-BE-30a-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create annual review cycles | Design annual review process and assign ownership | Consultant | Single | No | Dependency | A-BE-30a-01, A-BE-28b-02 | No
A-BE-30a-03 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create annual review cycles | Document and hand off to client | Consultant | Single | No | Dependency | A-BE-30a-02 | No
A-BE-30b-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create seasonal refresh cycles | Define seasonal refresh calendar and triggers | Consultant | Single | No | Dependency | I-BE-16b-01 | No | Seasonal content program must be designed first
A-BE-30b-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create seasonal refresh cycles | Design refresh cycle process and assign ownership | Consultant | Single | No | Dependency | A-BE-30b-01, A-BE-28b-02 | No
A-BE-30b-03 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create seasonal refresh cycles | Document and hand off to client | Consultant | Single | No | Dependency | A-BE-30b-02 | No
A-BE-30c-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create evergreen maintenance cycles | Define maintenance triggers for evergreen content (condition, relevance, age) | Consultant | Single | No | Dependency | I-BE-16a-02 | No
A-BE-30c-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create evergreen maintenance cycles | Design maintenance cycle process and assign ownership | Consultant | Single | No | Dependency | A-BE-30c-01, A-BE-28b-02 | No
A-BE-30c-03 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create evergreen maintenance cycles | Document and hand off to client | Consultant | Single | No | Dependency | A-BE-30c-02 | No
A-BE-30d-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create reuse standards for retired assets | Define criteria for what retired assets are eligible for reuse | Consultant | Single | No | — |  | No
A-BE-30d-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create reuse standards for retired assets | Define reuse pathways (repurpose, donate, recycle) | Consultant | Single | No | Dependency | A-BE-30d-01 | No
A-BE-30d-03 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create reuse standards for retired assets | Document reuse standards and hand off to client | Consultant | Single | No | Dependency | A-BE-30d-02 | No
A-BE-30e-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Repurpose banners and decommissioned items | Inventory all decommissioned banners and items eligible for repurposing | Facilities / Client | Single | No | Dependency | A-BE-30d-01 | No | Facilities-led inventory
A-BE-30e-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Repurpose banners and decommissioned items | Evaluate repurposing options: creative reuse, donation, sustainable disposal | Consultant / Facilities | Single | No | Dependency | A-BE-30e-01 | No | Creative, sustainability, and facilities tracks all implied
A-BE-30e-03 | Advanced | Brand Expression | Content refresh and circular reuse systems | Repurpose banners and decommissioned items | Execute repurposing per chosen pathway | Facilities / Third-party | Single | No | Dependency | A-BE-30e-02 | No
A-BE-30f-01 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create material life-extension procedures | Define life-extension criteria and procedures per material type | Consultant | Single | No | Dependency | A-BE-30d-02 | No
A-BE-30f-02 | Advanced | Brand Expression | Content refresh and circular reuse systems | Create material life-extension procedures | Document procedures and hand off to client | Consultant | Single | No | Dependency | A-BE-30f-01 | No
A-BE-31a-01 | Advanced | Brand Expression | Cultural activation programs | Create rotating cultural activation program | Define program scope, themes, frequency, and locations | Consultant | Single | Yes | Dependency | I-BE-18a-02 | No | Recommendation — art strategy must exist first
A-BE-31a-02 | Advanced | Brand Expression | Cultural activation programs | Create rotating cultural activation program | Design program framework including scheduling, curation, and community partnership model | Consultant | Single | Yes | Dependency | A-BE-31a-01 | No | Recommendation — HR and community partnership implied
A-BE-31a-03 | Advanced | Brand Expression | Cultural activation programs | Create rotating cultural activation program | Brief client on program and transfer ownership for implementation | Consultant | Single | Yes | Dependency | A-BE-31a-02 | No | Handoff — client leads implementation
A-BE-31a-04 | Advanced | Brand Expression | Cultural activation programs | Create rotating cultural activation program | Client implements and operates rotating program | Client | Single | Yes | Dependency | A-BE-31a-03 | No | Client-led beyond handoff
A-BE-31b-01 | Advanced | Brand Expression | Cultural activation programs | Create employee participation activations | Define employee participation activation formats (events, installations, submissions) | Consultant | Single | Yes | Dependency | I-BE-18c-01 | No | Recommendation — builds on co-creation program
A-BE-31b-02 | Advanced | Brand Expression | Cultural activation programs | Create employee participation activations | Design activation framework and coordination model with HR | Consultant | Single | Yes | Dependency | A-BE-31b-01 | No | Recommendation
A-BE-31b-03 | Advanced | Brand Expression | Cultural activation programs | Create employee participation activations | Brief client and transfer ownership | Consultant | Single | Yes | Dependency | A-BE-31b-02 | No | Handoff — client leads
A-BE-31b-04 | Advanced | Brand Expression | Cultural activation programs | Create employee participation activations | Client implements employee participation activations | Client | Single | Yes | Dependency | A-BE-31b-03 | No | Client-led beyond handoff